## Sheet1
| HREiR Action plan template 2022-2024 |  |  |  |  | Add institutional logo
Details
| Institution name: | Diamond Light Source Ltd | The institutional audience* for this action plan includes:
| Cohort number: | 300 | Audience (beneficiaries of the action plan) | Number of | Comments
| Date of submission: | 2022-03-31 | Research staff | 41 | Post Doctoral Research Associates (PDRAs)
| Institutional context: | Diamond Light Source is the UK's national synchrotron light source science facility. Its purpose is to produce intense beams of light whose special characteristics are useful in many areas of scientific research. It is a not-for-profit organization. | Postgraduate researchers | 109 | PhD students
|  |  | Professional support staff | 150 | Facility support scientists and managers engaged in research (estimate)
Total number of researchers (staff & students)
|  |  | Percentage of researchers | 34% | Fraction of all staff & students required to carry out research.
Column1 | Obligation2 | Action | Success Measure (SMART) | Deadline | Responsibility | Progress update (to be completed for submission) | Outcome/result | Column2
Environment and Culture
Institutions must:
ECI1 | Ensure that all relevant staff are aware of the Concordat | Communicate at least annually via staff-wide communications (e.g. Learning at Work Week event) and report annually to Diamond Executive on progress of this action plan. | Executive accepts progress as good and worthwhile and supports continuing membership. Greater awareness by staff of the matters most relevant to them - next time we run CEDARS an improved awareness score by 5%. Records of staff accessing the resources from our Learning Management System increases by 2%. Improved top-level support and acknowledgement of HREiR. | 01/3/2023 (and annually) | Scientific Training Advisory Group (STAG) | Launched CEDARS Survey - more general comms on Vitae Concordat planned with outcomes. 2022 & 2024 L@WW Comms - done. Awareness of the Vitae concordat, from the CEDARS survey results, remains quite low but with a very modest increase: 21% in 2021, 22% in 2023. | We continue to sign up to the Concordat and Vitae membership. Only a 1% increase which is disappointing but the introduction of the PDRA Development document (see E16) will help in future. There is still more to do here and this will be carried forward in the new action plan to address the shortfalls. | e | New
ECI2 | Ensure that institutional policies and practices relevant to researchers are inclusive, equitable and transparent, and are well-communicated to researchers and their managers | Set up a Researcher audience in GEM to identify which staff members have research as an element of their Job role. | Implement the ability to automatically target researchers for relevant development. | 2023-08-01 | Head of Human Resources (HR)/OD Manager | Complete, but only 26 people signed up to date. No development signposted to date. We are pursuing new initiatives to obtain researcher names and numbers, including recording ORCIDs on HR systems. | Not yet actioned as very few researchers have signed up the audience, hence plan to develop a new method of recording which staff are researchers, via ORCID. Carried forward to new action plan [ECR4]. |  | P2.1 P6.8
ECI3 | Promote good mental health and wellbeing through, for example, the effective management of workloads and people, and effective policies and practice for tackling discrimination, bullying and harassment, including providing appropriate support for those reporting issues | Diamond Wellbeing Group to promote wellbeing activities across the year. An Anti-Bullying and Harassment Policy to be published and related training put in place. Offer Headspace mental health resource to all staff, and promote the Employee Assistance Programme Mental Health (Mindfulness) app. | Anti- Bullying and Harassment training completed by 50% of staff. EAP/ Headspace uptake & usage at least stable or increasing through increased awareness. | 2022-12-31 | Head of HR/Organisational Development (OD) Manager | B&H Policy published. Almost all staff have completed this training. Usage of EAP: 7% of staff have accessed the EAP in the last year to April 2023 and only 5.5% to April 2024. The most frequent use is re mental health ad then legal advice. Usage of Headspace: 18.5% of staff are registered users in 2022 rising to 26.5% as at a current date (including some family members). The equates to over 15K mins use per annum. The most used content is mediation and sleep. | This has been successful and is completed. Headspace usage is gradually increasing and providing a range of support including that associated with self-care and management e.g. meditation and sleep both of which will help mental health (the highest use of EAP). The EAP access remains low but is serving a useful and important support mechanism for those with mental health challenges. |  | P6.9 | HR asked (again) 23/9 and 10/10
ECI4 | Ensure that managers of researchers are effectively trained in relation to equality, diversity and including, wellbeing and mental health | Ensure EDI training is offered, communicated well. Endeavour to have good attendance. | EDI Training sessions are at least 75% of maximum capacity and evaluations are good. The EDI questions ('I am treated with respect as an individual' and 'The company shows care and concern for its employees') included in the Employee Opinion Survey see a 5% improvement over the life of this action plan. | 2022-12-31 | Equality, Diversity & Inclusion (EDI) Manager | Training attendances is variable depending on topic but unlikely to be 75% of max capacity on average. Q re respect in 2022 EOS: 77% +ve Q re care & concern in EOS: 46% +ve. Q: Diversity in EOS: 73%.All show a sight decline from the 2020 survey which was generally very positive. | Training attendance has been good and achieved the target on average. This shows good engagement with the topic and a raised awareness across the Company. Some of the scores, although generally high, were not wholly positive and changes within the organisation has had an overall impact on motivation and morale. The 2020 survey did have a positive glow due to covid effects (nationally we are told so we are not concerned about the slight decline. We are running another survey in 2023 so can look at the results here too. |  | P2.3
ECI5 | Ensure that researchers and their managers are aware of, and act in accordance with, the highest standards of research integrity | Ensure that all research staff are aware of Diamond's 'Code of Best Practice in the Conduct of Scientific Research'. | Implement new online process for raising this awareness. More than 90% scientific staff to record completion. At least two comments/suggestions received for proposed new text. | 2023-04-01 | Legal/OD Team | Now in GEM (annual refresher). 66% of all staff have completed it. All staff are asked to complete the most basic level of training as an introduction to the management of scientific integrity. | This is positive as a new initiative. There is likely more to be done to encourage more staff to complete. The scientific staff are likely to engage with it more proactively s they can see the direct link to their work, whereas the more corporate functions less so. |  | P6.1
ECI6 | Regularly review and report on the quality of the research environment and culture, including seeking feedback from researchers, and use the outcomes to improve institutional practices | Participate in CEDARS survey and publish results and summary. Review annual Employee Opinion Survey (EOS) data for Science Divisions in particular compared with the rest of the Organisation to identify any issues with this group of employees. Research staff are consulted via their STAG representatives on the contents of Diamond's Research Culture statement. | At least 70 researchers to participate in survey. Results published on STAG pages and summarized in Organisational Development Working Group minutes (available on intranet). EOS results published and analysed at Divisional Level for any specific issues/anomalies. Improved focus on areas where Diamond falls bellow best practice and standards. | 2022-04-01 | STAG/OD | Complete. Good EOS completions rates in 2022 EOS for Science (Life-66% (171) and Physical-69% (144). Specific issues being Identified. CEDARS survey run Summer 2023 completed by 77 of our research staff. | EOS and CEDARS surveys have had good completion rates and the outcomes have been embedded within this and other action plans to ensure our staff are listened to and actions arise from their feedback. All actions plans are published so staff can see progress. |  | P6.10 P7.5
Funders must:
ECF1 | Including requirements which promote equitable, inclusive and positive research cultures and environments in relevant funding calls, terms and conditions, grant reporting, and policies | [7 empty] | P6.6
ECF2 | Consider how funding opportunities and policies can facilitate different patterns and ways of working, and promote the wellbeing and mental health of researchers | [7 empty] | New
ECF3 | Ensure that funding call requirements and selection processes offer equality of opportunity between different groups of researchers, recognise personal contexts, and promote positive research cultures and working conditions | [7 empty] | P6.6
Managers of researchers must:
ECM1 | Undertake relevant training and development opportunities related to equality, diversity and inclusion, and put this into practice in their work | Ensure mandatory EDI training is carried out by all staff. Deliver neurodiversity training for managers annually. | >90% uptake recorded. 20 or more managers attend the neurodiversity session annually | 2022-12-31 | EDI Manager | 100% of staff have completed the mandatory EDI training. Manager Neurodiversity training delivered to: 2022: 31 and 2023:34. In addition we have added 2 new elearning resources: Supporting Neurodiversity in the workplace and Understanding Neurodiversity in the workplace. | We have successfully achieved the EDI training partially due to its mandatory nature and embedded within he new starter processes for new staff. To date we have also achieved delivery of at least 20 managers attending/completing neurodiversity training annually. This will have raised awareness of the issue which is more prevalent woithing Demand than many other organisations (at least 12% o our staff are self- identified as neurodiverse; the actual figure is believed to be much higher). |  | New
ECM2 | Ensure that they and their researchers act in accordance with the highest standards of research integrity and professional conduct | Ensure they are familiar with Diamond's 'Code of Best Practice in the Conduct of Scientific Research'. | >90% completion recorded | 2023-03-31 | STAG/Legal/OD Manager | 84% (714) staff have now completed this elearning. Those staff that have not appear to be predominantly low level administrative staff. | We consider this action complete for now but will continue to promote and encourage completion by our scientific staff in particular. This will ensure standards and integrity are maintained at the high level. |  | New
ECM3 | Promote a healthy working environment that supports researchers' wellbeing and mental health, including reporting and addressing incidents of discrimination, bullying and harassment, and poor research integrity | [7 empty] | P6.9
ECM4 | Consider fully, in accordance with statutory rights and institutional policies, flexible working requests and other appropriate arrangements to support researchers | [7 empty] | New
ECM5 | Engage with opportunities to contribute to policy development aimed at creating a more positive research environment and culture within their institution | Managers to ensure that staff are aware of their representatives on the Scientific Training Advisory Group (STAG) and encourage them to raise topics for STAG and Organisational Development Working Group. | STAG group to receive at least 2 new topics for discussion annually via science group representatives. | 31-Sep-22 (and ongoing) | STAG | Results of the CEDARS 2023 survey were presented at the 2024 Learning at Work event, which promoted Vitae and generated interest and some good interaction (with over 25 employees). STAG reps have been active in proposing topics. The most recent meeting considered several, including publication authorship & recognition, and possible cuts to the PDRA programme. Both have been brought to the ODWG for discussion. |  |  | New
Researchers must:
ECR1 | Actively contribute to the development and maintenance of a supportive, fair and inclusive research culture and be a supportive colleague, particularly to newer researchers and students | [7 empty] | New
ECR2 | Ensure they act in accordance with employer and funder policies related to research integrity, and equality, diversity and inclusion | [7 empty] | P5.3
ECR3 | Take positive action towards maintaining their wellbeing and mental health | Attend/complete the training provided by Diamond which support wellbeing and good mental Health e.g. Stress Awareness, Resilience, Time Management, Mindfulness, Positive mental Health at Work (for both individuals and line managers) | Records of attendance show a year by year increase in people being trained in these areas. | 31-3-23 (and annually reporting) | All Researchers/ OD Team reporting | Attendance/completion for 2022 , 2023 & 2024 as follows: Stress Elrg - increased by 62%. Stress workshop - Instead of the face to face courses, we have added 7 stress elearning resources to our LMS instead . Resilience - no courses run but we Time Management Workshop - This is been replaced by elearning. Time Mgt Elrg - 6% of staff have completed this new elearning to date. Mindfulness - low completion rates but possibly due to there resources and support available within the Headspace app. Positive Mental Health at Work elrg - This has not increased but stayed reasonably static albeit low. In addition we have added 15 new stress/resilience elearning resources to GEM LMS. Also a further 4 time mgt resources to replace the face to face sessions. We have also trained Mental Health First Aiders. | The increase identified is hard to measure as the goal posts have changed. We now have multiple elearning courses for people to access rather than one face to face course. The main psotrive is that people continue to access the training available to them to support their own wellbeing. |  | New
ECR4 | Use available mechanisms to report staff who fail to meet the expected standards of behaviour, particularly in relation to discrimination, harassment, bullying, and research misconduct | [7 empty] | P6.9
ECR5 | Consider opportunities to contribute to policy development aimed at creating a more positive research environment and culture within their institution | [7 empty] | P3.13
Employment
Institutions must:
EI1 | Ensure open, transparent and merit-based recruitment, which attracts excellent researchers, using fair and inclusive selection and appointment practices | [7 empty] | P1.2 P6.2 P6.7
EI2 | Provide an effective induction, ensuring that researchers are integrated into the community and are aware of policies and practices relevant to their position | [7 empty] | P3.6
EI3 | Provide clear and transparent merit-based recognition, reward and promotion pathways that recognise the full range of researchers' contributions and the diversity of personal circumstances | [7 empty] | P2.6 P6.3 P6.4 P6.7
EI4 | Provide effective line and project management training opportunities for managers of researchers, heads of department and equivalent | [7 empty] | P2.3
EI5 | Ensure that excellent people management is championed throughout the organisation and embedded in institutional culture, through annual appraisals, transparent promotion criteria, and workload allocation | [7 empty] | P2.6 P6.3 P6.4
EI6 | Seek to improve job security for researchers, for example through more effective redeployment processes and greater use of open-ended contracts, and report on progress | 1. Produce Post Doctoral Research Associate (PDRA) Support and Development document. 2. Produce PDRA (fixed-term) justification document with input from STAG and PDRA groups. 3. HR to carry out a review of the use and justification of fixed term contacts (FTCs). | Documents written, approved, published and publicized on intranet. Refer to this document in PDR (Performance & Development Review) of PDRAs (goal: > 50%); Review every two years. Review documented and shared with Exec and ERC. Aim for year-on-year reduction in fraction of posts being FTCs (currently 15%). Improved job-security for PDRAs. Improved career opportunities. Reduced unemployment in leaving Diamond. Improved reputation as employer of choice. Improvement in ability to recruitment. More fixed-term posts continued to end of contract. | 2023-02-01 | HR/OD Working Group/ STAG | 1. Document developed and published. 2. Completed and being implemented by HR. 3. Some info received from STAG researcher representatives & Student Engagement. No further action to date due to staff departures. | 1. The document with a checklist to support managers and PDRAs has been prepared and published on the Intranet.* We have not had a PDR process since the publication so cannot accesses its use in their formal(annual) process. 2. The justification document has been prepared, published and is being used by HR. It has not changed the number of FTCs we have but we are ensuring that thoughts goes into the decision making prior to appointing to such posts. This is key. The majority of our FTCs are PDRAs which benefit form FTCs. *we are additionally looking at how we might bring the paper-based documents for to life via our LMS. |  | P1.3 P2.1 P2.2
EI7 | Consider researchers and their managers as key stakeholders within the institution and provide them with formal opportunities to engage with relevant organisational policy and decision-making | [7 empty] | P3.13
Funders must:
EF1 | Include requirements which support the improvement of working conditions for researchers, in relevant funding calls, terms and conditions, grant reporting, and policies | [7 empty] | P2.4
EF2 | Review the impact of relevant funding call requirements on researchers' employment, particularly in relation to career progression and lack of job security | [7 empty] | New
EF3 | Support institutions to develop policies and frameworks to promote sustainable employment arrangements and enhance job security, and provide opportunities for career progression | [7 empty] | P2.4
EF4 | Consider the balance of their relevant funding streams in providing access to research funding and its impact at all career levels | [7 empty] | New
Managers of researchers must:
EM1 | Undertake relevant training and development opportunities so that they can manage researchers effectively and fulfil their duty of care | [7 empty] | P2.3
EM2 | Familiarise themselves, and work in accordance with, relevant employment legislation and codes of practice, institutional policies, and the terms and conditions of grant funding | [7 empty] | P2.2
EM3 | Commit to, and evidence, the inclusive, equitable and transparent recruitment, promotion and reward of researchers | [7 empty] | P6.3
EM4 | Actively engage in regular constructive performance management with their researchers | [7 empty] | P2.3
EM5 | Engage with opportunities to contribute to relevant policy development within their institution | [7 empty] | New
Researchers must:
ER1 | Ensure that they work in accordance with, institutional policies, procedures and employment legislation, as well as the requirements of their funder | [7 empty] | New
ER2 | Understand their reporting obligations and responsibilities | [7 empty] | New
ER3 | Positively engage with performance management discussions and reviews with their managers | [7 empty] | P5.6
ER4 | Recognise and act on their role as key stakeholders within their institution and the wider academic community | [7 empty] | P5.2
Professional and Career Development
Institutions must:
PCDI1 | Provide opportunities, structured support, encouragement and time for researchers to engage in a minimum of 10 days professional development pro rata per year, recognising that researchers will pursue careers across a wide range of employment sectors | More structured career development programme should be put in place for early stage researchers. 1. Career development pathways document developed and published. 2. Scientific Development Programme prepared and published | Career pathways published on intranet (including pathways specifically relevant to early career scientists). Draft of Scientific Development Programme prepared and discussed with STAG and ODWG for consultation on content etc. Once finalised run to meet demand - ideally for 10-15 Scientists annually. | 2023-12-01 | OD Manager (with input from Line managers, Student Engagement and STAG) | Key resource has left and not yet replaced. This work is still planned for the future. | This action has therefore had little impact to date. Carried forward to the new action as a result. |  | P3.1 P3.3 P5.5
PCDI2 | Provide training, structured support, and time for managers to engage in meaningful career development reviews with their researchers | [7 empty] | P3.10
PCDI3 | Ensure that researchers have access to professional advice on career management, across a breadth of careers | Develop and publish Scientist Development Toolkit with competencies: 1. Make available on intranet (STAG pages) 2. Review Toolkit every two years 3. Incorporate Toolkit into Diamond-wide competency framework 4. Publicise Vitae training resources and incorporate into Diamond Learning Management System (GEM). 5. Develop an internal secondment policy | Toolkit accessed more that 30 times per year. Updates appear in STAG page with date and request for comments and amendments. Diamond competency framework published and referred to in Job Descriptions. Vitae Resources accessed via GEM by at least 20 Scientists annually and a talk delivered annually on the resources available. Improved career progression for researchers via greater internal mobility (2 internal moves each year internally). | 1. 1/8/22 2. 1/4/24 3. 31/5/23 4. 1/6/22 5. 31/12/23 | STAG/OD | 1. Done 2. Last updated March 2024. 3. n/a at this time as DLS competency are not yet defined. 4.Complete 5. Drafted and awaiting approval from Head of HR and Exec Team. The existence of an informal secondment policy was highlighted at a 2024 Learning at Work session. All tasks completed except [3] and [5], which are carried forward to the new plan [e.g. PCDI5]. | Presentations on secondment, research leave and sabbatical opportunities were received with interested, generating a number of questions that the STAG group have taken to the Organization Development Working group. This has highlighted the fact that such initiatives are some of the highest priorities for researchers. |  | P3.1
PCDI4 | Provide researchers with opportunities, and time, to develop their research identity and broader leadership skills | Set up technical and scientific reports for work that is unlikely to be published through conventional channels in order to ensure all Diamond scientific and technical outputs are made public and that the authors are recognized. | In-house publication workflow is established, with documents assigned Digital Object Identifiers. At least 10 documents per year are published via this route. Publications are explicitly acknowledged in Personal Development Review (PDR). Scientific paper writing training provided with over 10 attendees and 80% satisfaction rate. Improved acknowledgement of scientific and technical publication. Improved dissemination of scientific and technical developments. | 2023-03-01 | STAG/OD | This work has stalled due to resources issues and Diamond II priorities. It has been carried forward to the new action plan. |  |  | P3.11 P3.14
PCDI5 | Recognise that moving between, and working across, employment sectors can bring benefits to research and researchers, and support opportunities for researchers to experience this | Update and publish a revised Secondment Policy & procedure. Publish revised research leave information. | Published and communicated. An uptake (post Covid) of 1-2 additional applications received. | 2022-07-01 | HR/Legal | Internal Secondment Policy awaiting approval. Awaiting corporate decision about external secondment, particularly for the Diamond dark period. | This has not been a priority and external secondment and global mobility is being incorporated into they Diamond II project. This has therefore carried forward to the new action plan [PCDI5]. | a | P3.2 P3.4
PCDI6 | Monitor, and report on, the engagement of researchers and their managers with professional development activities, and researcher career development reviews | Research output (papers and talks) are explicitly referred to in the Performance and Development Review (PDR) process. | PDR guidance updated. Improved recognition of research. | 2022-12-01 | HR/OD | Complete. | This ensures that scientists are recognised (at elast annually) formally for their contribution to papers, reports and talks. |  | New
Funders must: |  | #
PCDF1 | Incorporate specific professional development requirements in relevant funding calls, terms and conditions, grant reporting, and policies. This should include researchers' engagement in a minimum of 10 days' professional development pro rata per year, and evidence of effective career development planning | [7 empty] | P3.7 P3.9
PCDF2 | Embed the Concordat Principles and researcher development into research assessment strategies and processes | [7 empty] | New
PCDF3 | Acknowledge that a large proportion of the researchers they fund will move on to careers beyond academia, and consider how they can encourage and support this within their remit | [7 empty] | New
Managers of researchers must:
PCDM1 | Engage in regular career development discussions with their researchers, including holding a career development review at least annually | [7 empty] | P2.3
PCDM2 | Support researchers in exploring and preparing for a diversity of careers, for example, through the use of mentors and careers professionals, training, and secondments | [7 empty] | P3.4 P3.8 P5.5
PCDM3 | Allocate a minimum of 10 days pro rata, per year, for their researchers to engage with professional development, supporting researchers to balance the delivery of their research and their own professional development | [7 empty] | New
PCDM4 | Identify opportunities, and allow time (in addition to the 10 days professional development allowance), for their researchers to develop their research identity and broader leadership skills, and provide appropriate credit and recognition for their endeavours | [7 empty] | P3.6 P3.9 P5.5
PCDM5 | Engage in leadership and management training to enhance their personal effectiveness, and to promote a positive attitude to professional development | [7 empty] | New
Researchers must:
PCDR1 | Take ownership of their career, identifying opportunities to work towards career goals, including engaging in a minimum of 10 days professional development pro rata per year | Staff with a research element in their Job Descriptions to register as a researcher so this can be added to our learning Management system and them be notified of relevant learning opportunities | >75% Diamond researchers registered. | 2023-12-01 |  | See also EC12 above. | This is not complete as take-up has been low to date. Other methods are now being proposed as part of our forward plan, as this was unsuccessful. |  | P5.5
PCDR2 | Explore and prepare for a range of employment options across different sectors, such as by making use of mentors, careers professionals, training and secondments | [7 empty] | P3.8
PCDR3 | Maintain an up-to-date professional career development plan and build a portfolio of evidence demonstrating their experience, that can be used to support job applications | [7 empty] | P5.5
PCDR4 | Positively engage in career development reviews with their managers | Ensure that research output (papers and talks) is fully reported via the Performance and Development Review (PDR) process. Career aspirations are discussed as part of the PDR process also. | > 75% of research staff to report at least one scientific publication per year. | 2023-03-31 | Head of HR. Head of Comms. STAG. | In PDR form. Complete. Currently unable to report from PDRs. | The inclusion has been positively received by researchers but not by non-research staff who cannot identify with its inclusion. We are unable, with a paper-based process currently to report on the volume of publications annually. We hope to be able to do this in the future if the process moves online. |  | P3.10
PCDR5 | Seek out, and engage with, opportunities to develop their research identity and broader leadership skills | [7 empty] | P5.5
PCDR6 | Consider opportunities to develop their awareness and experience of the wider research system through, for example, knowledge exchange, policy development, public engagement and commercialisation | [7 empty] | P5.2
* The Concordat defines researchers as individuals whose primary responsibility is to conduct research and who are employed specifically for this purpose by a higher education institution or research institute. The primary audience is research staff, e.g. postdoctoral researchers, research fellows, research assistants. The Concordat encourages institutions to include other groups who actively engage in research as beneficiaries of their Concordat action plan. These could be postgraduate researchers; staff on teaching and research, or teaching contracts; clinicians; professional support staff; technicians.